## Sheet1
Sprint Backlog
Project: Library Management System
Team Members
Name | eMail | cellPhone | Other
Matt | mcash7@murraystate.edu
Epic 1 - Oct 16-Oct 22
Sprint 1
Story ID | Description of Work | Dependancies | Engineer Name | Score | Notes
1.1 | Book sorting psuedo code | Book class/mngmt | Matt | 2
1.2 | User and book mngmt psuedo code | None | " | 1
1.3 | Sprint backlog/planning | Some sort of forethought | " | 1
1.4
1.5
Epic 2 - Oct 30-Nov 5
Sprint 2
Story ID | Description of Work | Dependancies | Engineer Name | Score | Notes
2.1 | Psuedo into code | All psuedo code completed | Matt | 7ish
2.2 | Error handling | Concurrent with coding | " | 3
2.3 | Database structure design | None | " | 2 | Moved from sprint 1 due to time constraints
2.4 | GUI design | None | " | 1 | Moved from sprint 1 due to time constraints
2.5 | GUI psuedo code | GUI design | " | 3 | May bleed into sprint 3
Epic 3 - Nov 6-Nov 12
Sprint 3
Story ID
3.1 | Lot's more coding | None | Matt | 7
3.2 | GUI review / Possible changes | GUI code | " | 3
3.3 | Begin testing | Basic LMS running | " | 1
3.4
3.5
Epic 4 - Nov 13-Nov 26
Sprint 4
Story ID
4.1 | Definitely more coding | None | Matt | 5
4.2 | Documnentation for LMS | Mostly completed LMS | " | 4
4.3 | Further testing? | Incomplete testing | " | 1
4.4
4.5
Epic 5 - Nov 27-Nov 29
Sprint 5
Story ID
5.1 | Last minute emergency only coding | Complete failure | Matt | >9000
5.2 | Prepare demo | Completed LMS | " | 2
5.3
5.4
5.5